GitHub: https://github.com/qjmre23/Route2Zero   |   Live dashboard: https://route2zero.netlify.app/

TEAM LARPERS / ROUTE2ZERO / PILOT PLAN

# Team Larpers Pilot Plan

Route2Zero Six-Month City Pilot

City pilot question Can Route2Zero produce a city-owned, evidence-backed e-jeepney Phase-1 portfolio whose climate, equity, infrastructure, operator, and uncertainty assumptions have been tested against real local evidence?

# PILOT PURPOSE

Convert Route2Zero 2.0 from an evidence-based prototype into a locally validated planning workflow that cities can inspect, challenge, refresh, and own.

# PILOT SCOPE

Target up to three partner LGUs, subject to city pairing and pilot agreement.

Validate a manageable corridor sample, one flagship corridor, and a broader Phase-1 shortlist.

Engage relevant operators/cooperatives, a utility or energy counterpart, and rider/community representatives where appropriate.

Test ML service estimates, climate assumptions, route geometry, equity evidence, charging evidence, operator readiness, policy scenarios, robustness, and portfolio constraints.

# SIX-MONTH OUTCOME

| Outcome area | Deliverable |
| --- | --- |
| Decision | City-owned Phase-1 portfolio or shortlist with named next actions. |
| Evidence | Validated route cards, source registry, validation ledgers, and unresolved evidence owners. |
| Models | Calibrated service-intensity model, climate scenarios, model card, and evidence-confidence rules. |
| Operations | Scenario library, decision pack, refresh/retraining runbook, and reproducibility handover. |

# PILOT PATHWAY

| PROTOTYPE | VALIDATE | CALIBRATE | CO-DESIGN | HANDOVER |
| --- | --- | --- | --- | --- |

GitHub: https://github.com/qjmre23/Route2Zero   |   Live dashboard: https://route2zero.netlify.app/

SIX MONTHS / THREE EVIDENCE GATES

# Six months, three evidence gates

| Timeline | Activity / Milestone | Core activity | Outcome |
| --- | --- | --- | --- |
| Month 1 | Baseline + model protocol | Confirm decision owners and route sample; freeze source registry/build; approve validation, ML evaluation, privacy, and climate protocols. | Pilot charter; baseline build; route sample; validation protocol; risk register. |
| Month 2 | Data refresh + ground truth | Desk/field-check routes; observe service; validate geometry; collect operator, charging/depot, and local equity/accessibility evidence. | Updated validation, operator, and charging ledgers; ground-truth sample; source refresh. |
| Gate 1 | Evidence readiness review | Accept evidence plan and model-validation protocol; confirm minimum data coverage; resolve governance blockers. | Approved evidence gate or documented corrective actions. |
| Month 3 | Model + route validation | Compare ML estimates with refreshed observations; recalculate metrics; review anomalies; tune geometry/evidence rules and equity variables. | Pilot model evaluation; model-card update; revised evidence grades; validated flagship case. |
| Month 4 | Climate, charging + operator pre-feasibility | Calibrate diesel/electric assumptions; validate energy scenarios; request utility evidence; assess sites, operators, and verified constraints. | Calibrated climate scenario; charging/operator cards; optimizer-ready constraints. |
| Gate 2 | Quality + route-set review | Accept pilot route set and model/evidence quality; hold routes with unresolved critical issues or mark them evidence-limited. | Approved route set with explicit holds and evidence limits. |
| Month 5 | Scenario co-design + human factors | Run policy workshops; review sensitivity; agree portfolio constraints; test Priority vs Evidence vs Stability; review assistant and accessibility. | Approved scenarios; draft portfolio; usability and governance findings. |
| Month 6 | Decision pack + handover | Finalize portfolio, evidence queue, model card, source registry, refresh process, issue log, analyst training, and task ownership. | Accepted decision pack; final build; reproducibility package; city handover. |
| Gate 3 | Acceptance | City decision pack and reproducibility handover accepted by named decision owners. | Go-forward decision and accountable next-step owners. |

Baseline traceability: build r2z-16690ccbe328 | scenario scn-c46e1d86c1 | service model service-v1-266e0b1d

GitHub: https://github.com/qjmre23/Route2Zero   |   Live dashboard: https://route2zero.netlify.app/

VALIDATION / SUCCESS / RESPONSIBLE AI

# The pilot succeeds when the evidence and decision improve

# SUCCESS METRICS

| Measure | Pilot success evidence |
| --- | --- |
| Coverage | % pilot routes ground-checked; % shortlisted routes with complete evidence cards; critical gaps resolved. |
| Model | MAE/RMSE vs refreshed observations, improvement over baseline, and documented route-level residual review. |
| Decision quality | Evidence-grade improvement; ranking/portfolio stability before vs after validation; routes moved from evidence-limited to decision-ready. |
| Adoption | LGU/operator/utility interactions; planner task completion; understanding of Priority, Evidence, and Stability. |
| Handover | One accepted city decision pack and one completed reproducibility/refresh handover. |

# VALIDATION METHODS

Field observations; operator interviews; LGU review; utility evidence requests; data reconciliation; grouped holdout testing; scenario workshops; usability/accessibility testing; stakeholder review of the flagship corridor.

# RESPONSIBLE AI CONTROLS

No resident-level personal data are required for core analytics; stakeholder data are consent-based.

No hidden LLM score changes and no automatic funding or procurement decisions.

No individual poverty or informal-status inference from population density.

Stakeholders can challenge or replace evidence; an AI-disabled deterministic fallback remains available.

# RISK REGISTER

| Risk | Control / response |
| --- | --- |
| Historic route data | Use current-validation ledger and field checks; retain historic-only status until verified. |
| Weak ML performance | Prefer observed evidence; mark model experimental; compare with baseline. |
| Utility capacity unavailable | Show mapped proximity only; keep capacity NOT VERIFIED; request evidence. |
| Operator data unavailable | Keep neutral prior explicit and raise validation priority. |
| Sparse geometry / equity data | Use reliability/evidence grades; validate traces; avoid unsupported settlement claims. |
| AI/API unavailable | Serve structured deterministic fallback; scores, scenarios, and portfolio are unaffected. |
| Constraint conflict | Show infeasibility and binding constraints; never fabricate a portfolio. |

GitHub: https://github.com/qjmre23/Route2Zero   |   Live dashboard: https://route2zero.netlify.app/

TEAM STRUCTURE / PARTNERS / HANDOVER

# Named owners from data collection to city handover

# TEAM STRUCTURE

| Name | Role | Relevant background / experience / skills for this role |
| --- | --- | --- |
| John Marwin Ebona | Product & Pilot Lead | City coordination, decision question, gates, integration, decision pack, handover. |
| Prince Marl | Data, ML & Pipeline Lead | Source registry, feature store, service model, metrics, build manifest, refresh. |
| Joaquin Sarmiento | Transport & Field Validation Lead | Route sampling, observations, status reconciliation, assumptions, operator workflow. |
| Isaac Marcus | Engineering, Optimization & Deployment Lead | Dashboard, scenarios, optimizer, Netlify, Mapbox, reliability, fallback behavior. |
| Andrei Dela Cruz | Policy, Governance & Responsible AI Lead | Policy controls, decision rights, workshops, risk/change control, responsible AI. |
| Russel Mendez | Climate, Research & Evidence Lead | Climate/energy method, source validation, confidence framework, documentation. |
| Tj Moreno | Stakeholder & Partnership Lead | LGU, operator, rider/community, utility and finance coordination and consent. |
| JM Palaganas | QA, Testing & Documentation Lead | Testing, accessibility, artifact QA, claim-output checks, issue tracking. |
| Carl Nueva | Geospatial & Infrastructure Analyst | Geometry review, spatial joins, equity layers, charging/power evidence, map QA. |
| Curt Mathew Garcia | Frontend & UX Developer | Responsive Route Lens, portfolio UX, walkthrough mode, usability, accessibility. |
| Marck Morgado | Field Validation & Logistics Coordinator | Field schedules, forms, route-check records, evidence handoff, logistics. |

# PARTNER RESPONSIBILITIES

| Partner | Pilot responsibility |
| --- | --- |
| LGU | Define decision context, validate evidence, join scenario workshops, review outputs, accept handover. |
| Operator / cooperative | Validate operations, fleet/depot constraints, readiness, and feasibility. |
| Utility / energy | Review charging assumptions and flag formal capacity/interconnection studies. |
| Riders / community | Validate access concerns and challenge equity assumptions where relevant. |

# HANDOVER AND SCALE

Handover: final build, model card, source registry, validation ledgers, scenario library, decision pack, issue register, refresh/retraining runbook, governance notes, and a city owner for each unresolved issue. Scale requires local adapters, recalibration, and validation; the Metro Manila model is not copied unchanged.