ROUTE2ZERO PILOT EXECUTION PLAN

Route2Zero Pilot Plan

A six-month, evidence-first pilot for equitable e-jeepney corridor prioritization in Metro Manila

PILOT INTENT

Move Route2Zero from a transparent historic-data MVP to a city-validated decision-support process that identifies which corridors are ready for deeper electrification planning, what evidence is still missing, and who owns each next action.

| COVERAGE TARGET 3 spotlight LGUs | EVIDENCE STANDARD 100% source-labeled | DECISION OUTPUT 1 validated shortlist |
| --- | --- | --- |

# Pilot objectives

| Refresh the baseline | Confirm current route, service, operator, and depot evidence instead of treating the 2013-2020 feed as live service. |
| --- | --- |
| Co-design the ranking | Test criteria, weights, confidence language, and safeguards with city offices, operators, drivers, and rider/community representatives. |
| Validate feasibility | Screen shortlisted corridors for service continuity, depot and charging constraints, operator finance, and implementation dependencies. |
| Leave a maintainable tool | Hand over documented data, editable overrides, reproducible scripts, trained owners, and a prioritized next-phase roadmap. |

Proposed pilot period: six months after award. Exact dates, partner commitments, and city scope will be confirmed during mobilization.

ROUTE2ZERO PILOT EXECUTION PLAN

Activities and execution timeline

Five gated stages connect data refresh, co-design, field validation, decision packaging, and handover.

| Timeline | Activity / milestone | Outcome |
| --- | --- | --- |
| Months 1-2 | Mobilize, refresh, and agree Confirm pilot governance; inventory current route, fleet, ridership, settlement, depot, and grid evidence; agree validation protocol and safeguards. | Signed pilot charter; data inventory; GTFS refresh plan; ethics and risk register; workshop calendar. |
| Month 3 | Co-design the evidence model Run city, operator, and rider sessions; test scoring definitions and weights; populate operator-readiness evidence; log contested assumptions. | Validated criteria and evidence rubric; operator override register; documented weight proposals; community issue log. |
| Month 4 | Validate routes and charging feasibility Ground-check shortlisted corridors; verify stop order and service pattern; screen candidate depots, feeder constraints, tariffs, and charging operating windows. | Verified pilot-route geometry; depot/charging options matrix; updated confidence grades; routes removed or escalated with reasons. |
| Month 5 | Calibrate and package decisions Re-run scoring and sensitivity scenarios; produce city shortlists, policy briefs, finance questions, and implementation dependencies. | Decision-ready shortlist; sensitivity report; policy briefs; financing and procurement question set; dashboard release candidate. |
| Month 6 | Demonstrate, hand off, and decide scale Train city and partner users; conduct final review; compare outputs with stakeholder judgment; agree ownership and next-phase data sharing. | Pilot evaluation; trained owners; handover pack; public methodology; scale/no-scale decision and 12-month roadmap. |

Decision gates

| GATE 1 · END M2 Enough current evidence to begin co-design | GATE 2 · END M4 Shortlist survives route and depot validation | GATE 3 · END M6 Named owners and data-sharing path support scale |
| --- | --- | --- |

ROUTE2ZERO PILOT EXECUTION PLAN

Workstreams, deliverables, and acceptance

Each workstream has a named evidence boundary and a concrete handoff.

| Workstream | Core activities | Deliverables | Acceptance test |
| --- | --- | --- | --- |
| A · Data and model | Refresh GTFS and reference layers; maintain provenance; run sensitivity analysis; protect nulls and proxy labels. | Versioned data inventory, reproducible pipeline, score cards, confidence ledger. | Every score traces to source, proxy, placeholder, or explicit missing state. |
| B · City and community validation | Facilitate LGU, operator, driver, and rider sessions; verify route realities and equity concerns; record disagreement. | Workshop records, validated issue map, equity evidence requests, agreed review criteria. | No corridor is called ‘equitable’ solely from WorldPop density. |
| C · Grid and depot feasibility | Screen candidate depots, charging windows, distribution constraints, tariffs, resiliency, and solar/storage pairing. | Depot options matrix, utility question list, interconnection risks, refinement backlog. | Regional grid share is never presented as local charger capacity. |
| D · Decision products and adoption | Publish city views, briefs, exportable rankings, training, governance, and scale decision pack. | Dashboard release, policy briefs, operator override workflow, handover and roadmap. | A city user can reproduce, challenge, export, and update the shortlist. |

# Success measures

| Measure | Pilot target | Evidence |
| --- | --- | --- |
| Data transparency | 100% of scored fields retain source and confidence labels | Automated data audit and route-level export |
| Stakeholder validation | At least one structured validation cycle per spotlight LGU | Attendance, issues, decisions, and unresolved items log |
| Decision usability | Partner users can filter, challenge weights, export, and explain a shortlist | Observed task test and closing survey |
| Handover readiness | Named owners for data refresh, overrides, and public methodology | Signed handover and 12-month roadmap |

ROUTE2ZERO PILOT EXECUTION PLAN

Team structure · Product and evidence

Role allocations define pilot accountability. Personal biographies and CV evidence can be appended if requested by the organizers.

| Name | Pilot role | Relevant skills applied / accountable outputs |
| --- | --- | --- |
| John Marwin Ebona | Project Lead and Policy Integration | Project coordination, decision framing, partner governance, risk escalation, and final pilot acceptance. Accountable for charter, decision gates, and scale recommendation. |
| Prince Marl | Lead Data Engineer | Data ingestion, validation, reproducibility, source controls, processed outputs, and operator-override workflow. Accountable for pipeline reliability and audit results. |
| Joaquin Sarmiento | Geospatial and Transport Analytics Lead | GTFS route logic, representative trips, geometry confidence, route-city tagging, field-validation protocol, and corridor map QA. |
| Isaac Marcus | Product and Streamlit Lead | Responsive dashboard, filters, accessible visualizations, export flows, offline-safe behavior, product analytics, and partner usability testing. |

# Core operating cadence

| Cadence | Participants | Purpose |
| --- | --- | --- |
| Weekly delivery review | All workstream leads | Evidence progress, blockers, data changes, and next seven-day commitments. |
| Biweekly partner clinic | Project lead + relevant city/operator leads | Resolve evidence requests and validate product decisions. |
| Monthly gate review | Project lead, partner sponsors, all accountable leads | Approve continuation, scope changes, risk treatment, and public outputs. |

ROUTE2ZERO PILOT EXECUTION PLAN

Team structure · Climate, equity, partnerships, and assurance

Cross-functional review keeps the model useful without overstating the evidence.

| Name | Pilot role | Relevant skills applied / accountable outputs |
| --- | --- | --- |
| Andrei Dela Cruz | Climate and Grid Research Lead | DOE source review, grid/emission-factor interpretation, charging evidence framework, climate-method boundaries, and utility/depot refinement questions. |
| Russel Mendez | Equity and Community Engagement Lead | Inclusive workshop design, rider/community evidence, equity safeguards, contested-assumption log, accessibility needs, and validation of density-proxy limitations. |
| Tj Moreno | Operator and Pilot Partnerships Lead | Cooperative engagement, fleet and finance readiness rubric, operator overrides, partnership follow-up, implementation dependencies, and workshop logistics. |
| JM Palaganas | QA, Documentation and Demo Lead | Test plan, issue tracking, browser and data QA, methodology/readme maintenance, submission artifacts, training materials, and live-demo readiness. |

# Decision rights

| Decision | Recommends | Approves | Required consultation |
| --- | --- | --- | --- |
| Data/source change | Data + domain lead | Project Lead | Affected workstreams |
| Score definition/weight | Analytics + equity leads | Monthly gate review | LGU, operator, rider/community participants |
| Public route shortlist | Product + policy leads | Partner sponsor + Project Lead | All evidence leads |
| Pilot scale decision | Project Lead | Partner sponsors | All workstreams and pilot users |

Role assignments can be adjusted during mobilization, but every workstream, decision gate, and published artifact must retain one accountable owner.

ROUTE2ZERO PILOT EXECUTION PLAN

Risk management, handover, and scale path

The pilot treats evidence gaps as managed work—not as numbers to fill silently.

| Risk | Level | Treatment | Owner |
| --- | --- | --- | --- |
| Historic or incomplete route data | High | Refresh priority routes with LGU/operator evidence; retain date and geometry confidence on every record. | Lead Data Engineer |
| Equity proxy misread as settlement truth | High | Use community validation; prohibit claims beyond density exposure; add missing-state language where needed. | Equity Lead |
| Grid score mistaken for local capacity | High | Pair every shortlist with depot/feeder questions; keep regional score constant and visibly coarse. | Climate/Grid Lead |
| Operator participation or finance evidence delayed | Medium | Keep neutral placeholder; schedule early clinics; document nonresponse; avoid forced precision. | Partnerships Lead |
| Model weights become political black box | Medium | Publish default and alternate scenarios; log who proposed changes and why. | Analytics Lead |
| API failure during demonstration | Low | Cache selected AI narratives and retain deterministic offline explanations for every ranked route. | Product Lead |

# Handover package

| OPERATE Runbook, environment setup, data refresh, overrides, tests, and issue log | GOVERN Source ledger, weight decisions, public methodology, risk register, and named owners | SCALE Validated gaps, partnership map, 12-month roadmap, resource ask, and replication checklist |
| --- | --- | --- |

# End-of-pilot recommendation

Scale only if the refreshed route baseline, community review, depot feasibility, and operator evidence materially improve confidence in the shortlist—and if named partner teams can maintain the data and governance after the hackathon team steps back.

Prepared 14 August 2026 · Route2Zero Team